## Sheet1
ID | Type | Description | Solution | Resolved
1 | Bug | Double fault when entering VM86 in Bochs and VirtualBox | Loading kernel segments (DS, ES, FS, GS) on interrupt resolved issue | TRUE
2 | Bug | Cannot load drivers using command line |  | FALSE
3 | Bug | AHCI driver broken | Fixed. | TRUE
4 | Bug | Cannot read from CD-ROMs | Fixed by itself | TRUE
5 | Bug | XADD emulation broken | Removed | TRUE
6 | Request | CMPXCHG emulation | Removed | TRUE
7 | Bug | Need to press a key to start on Virtual86 |  | FALSE
8 | Request | Move system calls out to files |  | FALSE
9 | Request | Validate system call inputs and pointers |  | FALSE
10 | Request | Stop executing RDMSR with MSR_APICBASE so often |  | FALSE
11 | Bug | APIC bogus vector 0, ignoring… (Bochs) |  | FALSE
12 | Bug | Bitblit very slow on non-QEMU emulators, especially on window moves, where bitblit ends up calling putpixel |  | FALSE
13 | Request | Add DEL command to command.exe |  | FALSE
14 | Bug | Environment variables not working (reading them crashes system) |  | FALSE
15 | Request | User mode environment variables missing |  | FALSE
16 | Request | Need to load PCI mappings from ACPICA | Done | TRUE
17 | Bug | CD-ROM writes work according to te.exe | Added writing failure message to te.exe, also made ISO9660::open() fail with WriteProtect if the mode != Read | TRUE
18 | Bug | Copying from source on another drive broken in command.exe |  | FALSE
19 | Request | RTC writing the time |  | TRUE
20 | Request | command.exe set time / date |  | TRUE
21 | Request | Add set date / time to init.bat |  | TRUE
22 | Bug | Doing some things with CD files crashes (e.g. type D:/TRANS.TBL) |  | TRUE
23 | Bug | Reading non-existant CD-ROM files goes on forever | Fixed by itself? | TRUE
24 | Critical | memcpy is broken | Replaced with unoptimised version | TRUE
25 | Request | Implement timezones |  | FALSE
26 | Bug | PCI assumed to exist | Detection code added | TRUE
27 | Bug | PCI mechanism #1 always used |  | FALSE
28 | Bug | ACPICA PCI tables crash upon being loaded | ACPICA.SYS was told its root was 'computer' when it was actually 'computer->root', causing it to cast a Computer to an ACPI, which obviously fails | TRUE
29 | Request | Optimise memcpy (properly though) | Done | TRUE
30 | Critical | ACPICA.SYS, VGA.SYS, VESA.SYS crashes | Fixed problem with SATA writes with counts > 16 | TRUE
31 | Bug | ATA reads with multiple sectors don't work correctly | The driver incremented the buffer by 1024, not 512 due to REP INSW being used | TRUE
32 | Request | Read VCACHE | Done | TRUE
33 | Bug | SATAPI and ATAPI are very sketchy when the disk is ejected |  | FALSE
34 | Bug | SATAPI can cause boots to hang on real hardware |  | FALSE
35 | Bug | Cannot boot / install on very low memory systems even with swapfile |  | FALSE
36 | Bug | Directories always exist, e.g. you can CD to an invalid directory, cannot use MKDIR because already exists |  | FALSE
37 | Request | VCACHE is horribly terrible at caching anything |  | FALSE
38
39
40